| Version | Issued | Approved by: | Role | Signature |
| --- | --- | --- | --- | --- |
| 1.0 | 28/06/17 | James Weeks | H&S and Incident Manager |  |
| 2.0 | 12/04/18 | James Weeks | H&S and Incident Manager |  |

Health & Safety  Policy & Arrangements

Show Address Clovelly Court, Clovelly, Bideford, Devon EX39 5TA. Grid Ref SS 309 252

Primary contact: Show Secretary, Mrs Andrée Carter 01409 240328 or 07595 919006

Churston Ford, West Putford, Holsworthy, Devon EX22 7UU

|  | Page |
| --- | --- |
| HEALTH AND SAFETY POLICY STATEMENT Show Committee’s declaration of intent on behalf of the Company | 2-3 |
| 1: Roles and responsibilities | 4-7 |
| 2. Arrangements for health & safety | 8-27 |
| 3: Exhibitors and contractors | 10 |
| 4: General traffic management | 11 |
| 5: First aid and accidents | 12 |
| 6: Fire precautions | 13 |
| 7: Electrical safety | 15 |
| 8: Temporary buildings and structures | 16 |
| 9: Environmental management | 17 |
| 10: Health hazards | 18 |
| 11: Catering | 19 |
| 12: Animals, Livestock and Equestrian events | 20 |
| 13: Security | 21 |
| 14: Plant and machinery | 22 |
| 15: Work at height | 22 |
| 16: Lifting operations | 22 |
| 17: Manual handling | 23 |
| 18. Children’s Entertainment | 24 |
| 19. Smoking | 24 |
| 20. Communications & Emergency Contacts | 24 |
| Annex 1 - Emergency Telephone Numbers | 25 |
| Annex 2 – Relevant Legislation | 26 |
| Annex 3 – Site Map | 27 |

Table of Contents

Health and Safety Policy Statement

The Woolsery & District Agricultural Show Executive acknowledges its legal and moral responsibilities for ensuring the safety, health and welfare of all persons who could be affected by the activities of the show and the environment it is held within.

Planning for the show is developed on an ongoing basis with continual improvement being a primary element in the commitment to delivering an enjoyable event for all people providing a service or attending, with due consideration for their health, safety and welfare.

The Executive will strive to effectively communicate the policy and ensure that all officials, contractors and others who may be working on behalf of the Show, in a paid or voluntary capacity, fully understand the requirement on their part in carrying out the policy and that their activity is undertaken in a manner which does not expose themselves or others to risk.

This general policy statement provides a commitment and intent to comply with the Health and Safety at Work Act 1974 and to promote industry best practice. To ensure the principles of health and safety are clearly understood by those involved in the operation of the Woolsery and District Agricultural Show we are committed to:

- Complying with relevant health and safety legislation, industry best practice and other agreements on health and safety and other requirements to which the society subscribes.

- Effective communication of and consultation on health and safety matters throughout the organisation and on the Show site.

- Due diligence in the monitoring and auditing of health and safety of those providing trading, catering, exhibition or features for public enjoyment.

- Assessing the risks to the safety and health of our officials, volunteers and others who may be affected by our activities and implementing controls to minimize those risks.

- Preventing injuries, ill health, disease and incidents associated with the activities of the organisation in its operation of the Show.

- Providing and maintaining safe plant and equipment and implementing safe systems of work.

- The safe use, handling, storage and transport of articles and substances.

- Providing and maintaining a safe working environment with safe access, egress and welfare facilities.

- Providing our offiials, stewards and volunteers with such information, instruction, training and supervision as required, to deliver a safe environment for those trading, exhibiting, participating in or visiting the Show.

- The organisation will also bring to the notice of contractors, exhibitors, caterers and other participants their duties under relevant health and safety legislation to those affected by their activities.

- Continually improving our health and safety management.

- Ensuring the necessary resources in the form of finance, equipment, personnel and time to ensure the health and safety of our officials, stewards, volunteers and others involved in the operation and participation of the Show.

- Seeking expert help where the necessary skills are not available within the Society.

- An annual review and where necessary, the revision of the Health and Safety Policy.

- The Executive and its committees will liaise with relevant external bodies and neighbouring parties to ensure that the impact on the locality in terms of safety and environmental matters is effectively and efficiently managed and any associated risk minimised.

- The Executive supports its considerable knowledge and experience of event safety by the appointment of a suitably competent Health and Safety and Incident Manager to provide advice on safety and incident management matters and general health and safety assistance.

- This policy will be made available by email or hard copy to all relevant interested parties as appropriate and through the Woolsery & District Show website.

The overall responsibility for compliance with Woolsery & District Show's Health and Safety Policy rests with the Show Chairman.

Mrs Pat Martin, Show Chairman

April  2018

1.0 Organisation

Figure 1. Management Structure and Show responsibilities

1.1 Roles and responsibilities

1.2 Chairman and Executive

- Overall responsibility for ensuring the arrangements detailed in the policy are implemented and achieving the objectives contained in the health and safety policy statement.

- Ensure that appropriate and adequate resources are made available to implement the policy.

- Ensure that the appropriate competency is provided to advise and assist in health and safety matters.

- Ensure the policy is effectively communicated to all relevant parties affected by the activities of the show.

- Establish an effective means of feedback from key people to provide information for reviewing the adequacy of the arrangements for health and safety for the show.

- Ensure that the policy is reviewed annually.

- Promote the Woolsery & District Agricultural Show’s commitment to health and safety at all times.

1.3 Show Committees

- Effectively support the Executive in achieving the objectives and implementing the arrangements contained within the policy.

- Committee members shall make themselves familiar with the content of the health and safety policy and other appropriate safety documents so as to be able to ensure activities within areas of responsibility are performed in compliance with the documented requirements.

1.2 Showground Directors and Deputies (Incident Management Team)

- Effectively support the Executive in achieving the objectives and implementing the arrangements contained within the policy.

- Ensure that exhibitors have full understanding of the need for risk assessments to contain sufficient detail so as to minimise the risk of harm to themselves and others who may be affected by their activities before applications are accepted.

- Liaise with the relevant Secretaries with regards to the engagement of contractors or other companies/persons providing specialist services for the society.

- With the relevant Secretaries, ensure that companies or individuals who are engaged to provide paid services to the society have the necessary competency to provide such services properly and safely.

- Through the Secretary, ensure that persons providing services to the society on a voluntary basis are provided with adequate instruction, information and support to allow them to execute their roles successfully.

- This will include Stewards being issued with a written statement of their duties, and where appropriate a checklist and a layout plan showing the key features of the site … and … receiving a final briefing of their duties on the day of the event.

- Ensure that the key findings of risk assessments carried out by the society are effectively communicated to any person(s) affected by its activities.

- If significant policy related issues are identified between review dates, ensure the Executive is informed as to the matter in a timely manner to allow for policy revision if necessary.

- Provide the Executive with costs and anticipated benefits for actions deemed necessary to improve health and safety.

- With the Showground Chairman and Show Secretary, carry out a post event H&S and incident management review to determine the success or otherwise of the arrangements. Based upon the review prepare a report for the council summarising the findings.

- Effectively disseminate the post show findings to ensure that any remedial actions identified in the report are addressed by the appropriate person(s).

- Undertake a post event review and analysis of accident/incident reports and investigations.

- Oversee the setting up, breakdown and dismantling phases of the show.

- Ensure that contractors understand the requirement to provide suitable and sufficient risk assessments and method statements identifying all significant hazards and risks and the required control measures relating to their activities.

- Liaise with the show council and committees on all health, safety and welfare matters relating to the showground and persons in attendance.

- Liaise with the Showground Chairman and Show Secretary on show day to ensure controlled, effective and dedicated channels of mobile and static communication are in place, and are used properly.

- Ensure that appropriate and adequate visual information for the public is strategically and clearly displayed.

- Ensure that emergency routes are clearly identified and that contingency plans are in place to ensure a clear passage for emergency services vehicles should an emergency condition arise.

- Manage the setting up of the showground in accordance with design drawings or instructions and meeting timescales.

- Manage the breakdown, dismantling phases of the show in line with laid down timescales for completion.

- Co-ordinate the activities of exhibitors and contactors in line with society rules and laid down procedures.

- Co-ordinate the activities and movement around the site of service providers

- Ensure that suitable arrangements for welfare, sanitation and waste management are in place.

- Promote the Woolsery & District Agricultural Show Society’s commitment to health and safety at all times.

1.3 Incident Management Team

- Be the first point of contact with police, local authority, other official or enforcement bodies, emergency services and local service providers.

- Enact the procedures described in the Woolsery Show Incident Response and Management plan.

1.4 Stewards

It is a general requirement of stewards that they shall:

- At all times be alert to potential hazards and take steps to mitigate or minimise and eliminate them.

- Be properly equipped and dressed for the event and being easily identifiable, e.g. wearing fluorescent jackets, tabards or arm bands etc.

- Have received adequate training and instruction to carry out their duties effectively.

- Have a full understanding of what action to take in an emergency including the use of coded messages.

- Assist the emergency services as required.

- Be aware of the location of the entrances and exits, first aid posts and fire-fighting equipment.

- Know the layout of the site and be able to assist the public by giving information about the available facilities, remembering especially people with disabilities.

- Recognise crowd conditions so as to ensure the safe dispersal of spectators and the prevention of over-crowding.

- Ensure that circulation areas and exits, including entrances and exits for emergency services are kept clear at all times.

- Be able to handle conflict or threatening situations in a controlled manner so as to prevent escalation of the situation.

- Not consume alcohol until completion of duties

1.5 Showground Volunteer

- Additional volunteers may assist with Showground set up, support on the day or takedown. These volunteers must be instructed and directly supervised by a member of the Woolsery Show Committee.

1.6 Contractors/Sub-contractors

- Provide documented evidence of competency and suitability to undertake work on behalf of the Woolsery & District Agricultural Show.

- Have in place suitable arrangements for carrying out task specific risk assessments and producing method statements for work to be undertaken.

- Ensure that control measures identified by risk assessments are in place and adhered to.

- Ensure that work equipment is fit for purpose and where appropriate has certificated evidence of inspection, testing and examination.

- Ensure that all accidents involving its own employees are recorded by the contract company and investigated – this may include working in conjunction with the Showground Director (and Safety Advisor if an incident occurs during the show) to determine causation and developing an appropriate response.

1.7 Health & Safety and Incident Management Team

- Inspection of all exhibitors’ stands and equipment.

- Enforcement of safety standards.

- Auditing and monitoring documentation.

- Provide the Executive with advice and assistance on all matters relating to the management of health, safety and welfare for the show.

- Be in attendance and readily accessible during the main event.

- By undertaking regular safety tours of the showground throughout the show day, monitor the safety arrangements provided by the Society and those expected to be put in place by others, e.g. exhibitors, esp. trouble spots in regard movement of vehicles, livestock and people.

- Produce a post-show report for the members, detailing the key findings of the day.

- Liaise with the Showground Director, Chairman and Show Secretary to ensure accidents and incidents are reported and the appropriate level of investigation carried out.

- Annually review the health and safety policy and incident response and management plan and general showground risk assessment, based on observations during that year's show.

- Should amendments be made to the above documents, forward the amended versions to the Show Secretary who will arrange for key persons to check the documents before final sign off at senior level.

2.0 Arrangements for Health and Safety

2.1 Training and instruction

Appropriate training and instruction will be provided for all persons who have an active role in the organisation and facilitation of the show to ensure they have the necessary competency to execute their duties effectively.

Examples of pre-show training and instruction will include for general control of crowds; emergency response/actions, including escaped animals; methods of communication; key findings of the event risk assessment(s).

2.2 Stewardship and public safety

General arrangements:

- A 5 mph speed limit for any vehicles having to enter public areas shall be enforced.

- Ground conditions in public areas and access pathways are permanent pasture and depending on previous weather, may not be suitable for people with disabilities, wheelchairs, families with toddlers and pushchairs.

- Exit points shall be large enough to permit an orderly evacuation from the site in the event of an emergency.

- Where reasonably practicable the show site grass will be mowed to minimise the risk of tripping

- Dogs must be kept on a lead at all times and owners advised that they must not be left in vehicles.

2.3 Stewarding

- An appropriate number of adequately trained stewards will be provided for the security and control of the site and the attending public.

- The required level of stewardship is determined by assessment of the number of duties and tasks to be covered, including staffing entrances and exits; controlling access to attractions/activities; general crowd control; patrolling public areas; securing unauthorised areas; securing hazards; car parking duties; etc.).

- Due to the length of the event, consideration should be given to making sure extra stewards are available to allow others to take rest periods and comfort breaks etc.

- Contingency arrangements are made to cope with excess numbers of people in show areas. This may include the creation of holding and/or queuing areas.

2.4 Communication and information

- Communication amongst show officials and senior stewards is facilitated by the use of walkie talkies with dedicated channels.

- Stewards and others shall be trained/instructed in the correct use of radios, the selection of channels and laid down wording to be used in particular situations.

- General communication, announcements and information are provided for by a public address system and strategically located information boards and way finding signage.

2.5 Livestock movement

- When animals are being loaded and unloaded from road transport vehicles and when being moved en masse between standings and show rings, the areas of transit will be closed to public access and be controlled by stewards to prevent unauthorised access.

- Livestock vehicle movement and loading MAY NOT commence until 4pm, after the Grand Parade whereby livestock vehicles will leave the site via the Exit Gate 3.

2.6 Lost Children and Vulnerable Adults

2.6.1 Found Child Procedure

- Police/Stewards should make immediate contact with the lost Children point (Show Secretary’s Tent) in case the parent/guardian is there, to advise that the child has been found.

- The child is then to be escorted by a steward/police officer to the Show Secretary’s tent. If a police officer is not present, where possible the child must not be touched/carried and a female Steward or member of the public should be asked to accompany the party to the Show Secretary’s Tent.

- An Incident Report form is to be completed in the presence of the Steward/police officer to detail where the child was found.

- Ensure that the child is occupied and distracted with a DBS designated person reassuring them that everything will be ok and someone will be there for them soon.

- Control to give a description of the child but NO NAME. Or put a call out for the parent by name if the child can give this information.

- Inform the child that someone (mummy/ daddy/guardian) has been called and is on the way to collect them.

- Keep putting out calls at regular intervals through control on the main PA system.

- The Secretary should also issue details to all Police/stewards regarding the lost child in case they are contacted by a parent/guardian.

- No food or drink, except plain water should be given to the child in case of allergies.

- Parents/guardians/carers claiming the child must show a form of identification (A photo driving licence, passport or correspondence showing their name and home address) before the child is released. In the event of any uncertainty, it will be the responsibility of the Police to determine if the child should be allowed to go with the person who is claiming them.

2.6.2 Lost Child Procedure

- If a missing child report is made to Police/Stewards then they should contact the lost children point in the Show Secretary’s Tent to ascertain whether the child is there.

- If the child is there then parents/guardians should be directed/ escorted directly to the lost children point.

- If the child is not there, then parents/guardians should be directed to the lost children point to complete an Incident Report form with a description of the child.

- The Show Secretary should then issue a message to all Police/Stewards so that they can remain vigilant.

- No details of the lost child should be relayed over the PA without permission of the Police Officer in charge.

- Any Police officer/Steward finding the lost child must contact lost children immediately. The child then must be immediately escorted to the Lost Child Point.

2.6.3 Found or Lost Vulnerable Adult

- The same procedures listed in sections 2.6.1 and 2.6.2 should be followed.

- A DBS approved person will be allocated to the vulnerable adult.

- It is important to remain calm, reassure and keep a close watch on the person until the police are notified and their guardian can be found.

- All details must be completed in the Incident Report Book in the Show Secretary's Tent.

3: Exhibitors and (their) contractors

- All exhibitors are required to comply with instructions given to them by officers and stewards of the society in regard show safety, failure to do so will result in removal from the show ground.

- All exhibitors will have completed a trade stand and fire risk assessment upon applying to exhibit.

- Trade exhibits are to keep strictly within their allocated site, in order to ensure free flow of spectators and if necessary, emergency vehicles. Exhibitors vehicles which cannot be accommodated are within the allocated space are to be removed to the public car park by 8.30 am.

- Exhibitors and contractors will provide their own public liability (and professional indemnity) insurance where appropriate.

- Larger exhibitors in terms of buildings/structures and activities, or the contractors engaged on their behalf, shall produce their own risk assessment which shall be provided to the Show Secretary as part of the application process to exhibit – Although not exhaustive, examples of this requirement would include the erection of large structures catering for the public and activities involving moving vehicles, machinery or mobile plant in close proximity to spectator areas.

- Exhibitors shall ensure that their activities, e.g. setting and up/dismantling of any structure, the laying out of wares, exhibits or delivery of demonstrations is carried out in accordance with site safety rules.

- Many of the arrangements for health and safety within the policy will be relevant and appropriate to exhibitors and contractors.

- Children are at particular risk during the setting up and taking down periods and it is advised that they are not brought to the ground at these times. If they are then an adult should supervise them at all times.

- Showground avenues must not be obstructed or encroached upon during the erection or dismantling of stand structures or by vehicles used in the course of erection to the detriment or inconvenience of other stand holders.

- Exhibitors engaging the services of others, e.g. contractors (companies or individuals) to carry out work on their behalf must ensure they have determined the competency of the person(s) to carry out the work properly and safely before engagement.

- If it is determined by show officials that contractors do not possess the necessary competency for the work engaged to carry out, then we retain the right to prevent such work commencing/continuing until a suitably competent person is engaged.

- Regular monitoring by the show officials will be carried out to ensure compliance with laid down standards is being met.

3.1 Accident reporting

- Show officials need to be notified of all accidents occurring on the showground and therefore companies engaging contractors to carry out work on their behalf will be responsible for reporting any accidents that come under the Reporting of Injuries, Diseases and Dangerous Occurrences Regulations (RIDDOR) Act.

- Accidents should be reported to the secretary’s tent so that appropriate action may be taken with regard emergency services and so that all details may be recorded into the accident book.

4: General traffic (road and off-road) management and car parking

4.1 Public roads

- The Show Secretary liaises closely with Devon County Council and local police to advise the date of the Show and that no road closures are required.

- Show Stewards have NO power to direct traffic on the public highway; they may only marshal traffic entering and leaving the site to ensure free and uninterrupted access so that traffic congestion does not occur.

4.2 Emergency services access and egress

- Gate 2 Clovelly Court Drive will be used for unobstructed access to and egress from site by the emergency services in the event of an accident or emergency. Stewards will be instructed by the Incident management Team to stop all other traffic.

- The emergency services are permitted to move vehicles in public areas during the event – for emergency purposes only.

4.3 Showground parking

  - Car parking areas are established well away from the main (pedestrian) areas of the showground and are clearly signposted.

  - Parking areas will have separate access and exiting points.

  - Stewards are allocated to provide control of car parking arrangements and for patrol purposes.

  - Unless authorised due to exceptional circumstances, the parking of cars anywhere else but in designated areas is not permitted.

  - Pedestrian routes from car parks to the show areas are clearly laid out with suitable and sufficient signposting.

  - Privileged parking arrangements will be made for disabled drivers who are blue badge holders near Gate 2. An appropriate car sticker must be displayed at all times.

4.4 Showground/Public areas

- Only the minimum necessary movement of vehicles will be allowed on site and a speed limit of 5mph shall be strictly enforced for the duration of on site activity.

- Dedicated safe access and egress routes will wherever reasonably practicable be designed into the showground layout.

- No vehicles of any type shall be moved around the showground between 8.30am and 5.30pm unless officially authorised.

- A properly insured licence holder may only drive vehicles.

- On site vehicles must not obstruct emergency exits.

- Exhibitors or contractors shall only be authorised to move vehicles (or mobile plant) in the hours laid down unless expressly authorised by show officials to the contrary.

4.5 Service vehicles

- There may be a requirement for vehicles servicing the event to operate on the showground during the public day, with examples being toilet management and food delivery.

- At all times service vehicles shall comply with the site speed limit and it must be ensured that standard vehicle warning systems are operating correctly.

- All-terrain vehicles/quad bikes:

- Whilst there is provision for ATVs/ quad bikes to be displayed on trade stands in static mode, the riding of them in public areas is not permitted in normal circumstances. If a quad bike has to be used the following conditions shall apply:

- The site speed limit must be complied with.

- Children under the age of 13 are prohibited from driving or passengering.

- Children aged 13 or over shall only be allowed to ride quad bikes of an appropriate size and power, and be able to provide evidence of formal training.

- Due consideration must be made for the noise potentially produced by a quad bike scaring horses/livestock and as such quad bike movement in or close to livestock areas shall be prevented or minimised to low speed and for a short duration, determined by necessity.

- Passengers should only be carried if the ATV is specifically designed for the purpose.

- Quad bikes must have proper grassland tyres fitted.

- Standard precautions for personal protection of the rider should be taken, whilst not a legal requirement the Executive would expect this to include properly fitting protective headwear being worn.

5: First aid and accidents

5.1 First aid

- Members of the ambulance service and a first aid team will be in attendance on the day of the show to provide first aid and stationed next to Gate 2 with a clear exit from the site.

- First aid posts shall be clearly identified and provided with easy access for all persons on the site and any attending ambulance at all times. Paramedics on site may be contacted via the show secretary on 07595 919006 or the walkie talkie.

5.2 Accident reporting and investigation

- An accident book and an incident report book (meeting data protection requirements) are provided in the site office and the Show Secretary’s marquee and they meet with data protection requirements.

- All incidents, involving injury or potential injury to persons (and damage to property or plant) occurring during the course of the event period, including the build-up and break-down, must be reported immediately to Show Secretary or Showground Manager or other nominated show official. The Safety Advisor shall also be informed at the earliest opportunity.

- The ambulance service in attendance will record the details of accidents, which they are required to respond to. The Show Secretary or other nominated council member will be responsible for liaising with them to ensure that details of accidents that may have not been notified to the show on the day are captured post show.

- Should any accident or dangerous occurrence (or show related disease) fall within the requirements for reporting under Reporting of Injuries, Diseases and Dangerous Occurrences Regulations (RIDDOR), then the Secretary and/or show Safety Advisor shall ensure that the any such report is made at the earliest opportunity and no later than within ten days of the occurrence.

- Should the severity of an accident or incident necessitate immediate reporting, this should be done telephoning 0151 922 9235.

- Internal recording of accidents/incidents shall include the date, time, location, and nature of incident, environmental conditions at the time and the names(s) and address(s) of all those involved, including witnesses and First Aiders.

- Where possible the immediate post event action should include sketches, plans and photographic or video evidence to assist the investigative process.

- The scale of any investigation will be proportionate to the incident.

- The Show Secretary, General Manager, Safety Advisor and a senior Council member where necessary will be responsible for investigating and recommending any preventative or necessary remedial action following any accident/incident.

5.3 Veterinary services

A Veterinary Surgeon, Horse Ambulance and Farrier are all in attendance and may be contacted via the show secretary on 07595 919006.

5.4 Fatality

In the event of sudden collapse it is recognised that the first response is likely to be to send for or attempt to apply first aid. Should it be determined that the person has died then the Police must be informed immediately and other than screening or covering the deceased person to minimise distress to others no other action shall be taken until the Police arrive at the scene.

6: Fire Precautions

6.1 General precautions

- In the event of a fire, dial 999, and immediately inform the Show Secretary on 07595 919006 or the allocated walkie talkie

- The alarm should be raised and neighbouring stands alerted to the risk. All trade stands are required to have their own appropriate fire extinguishers available for use at all times.

- Stewards, show officials and the safety officer shall undertake continuous monitoring of the event and its build up and break down looking for situations where combustible materials and/or flammable liquids are being stored or used in close proximity to potential sources of ignition or oxidising agents.

- Smoking is strictly prohibited in any enclosed structure or marquee.

- Fire extinguishers are located in a central station near the Secretary’s Tent.

- In the event of a fire the alarm will be raised manually with a handbell and announced on the public address system. A controlled evacuation of the area/showground shall commence under the control of show officials and stewards.

- Fire appliances should be able to access all parts of the site and be able to get within 50 metres of any structure.

- Established emergency access routes shall be kept clear at all times.

- Quantities of stored fuel for use with generators should be kept below 50 (fifty) litres or half a day’s supply, whichever is the lesser. The fuel container should be kept in a fire resistant construction.

6.2 Hazardous Equipment and Substances

- Particular care must be taken with the following potentially hazardous equipment. LPG Cylinders & Burners - Cylinders must be safely and securely stored. Exhibitors or contractors using liquefied petroleum gas (LPG) shall ensure that the gas and fittings/appliances are installed, stored and operated without risk to themselves or other persons.

- No smoking information shall be clearly displayed.

- Cylinders are to be positioned on firm level ground and at least 1m from vehicle openings and sources of ignition.

- If an LPG cylinder is stored in/on a vehicle, adequate ventilation must be provided to the vehicle compartment where an LPG fire appliance is located. This will include for fixed high and low vent openings being positioned so that they are not obstructed. Compressions fittings – Burners must be suitably sited and must have been examined and tested by a competent person and satisfactorily labelled to that effect. Documentation must be available for inspection on request.

- Electric Generators - These must be silent running, properly earthed and protected by an approved RCD Trip System.

- Leads and cables should be dug into the ground, the hot exhaust must be suitably directed and the generator must have been recently tested and labelled to that effect.

6.3 Catering

A fire risk assessment is required from any exhibitor planning to use heating (for hot refreshments or samples) or cooking appliances or hosting barbeque or open roasting (e.g. hog roast) events inside a tent or stand with fabric overlay.

The assessment shall include:

- Ensuring the area is laid out for purpose.

- Identifying types of equipment and/or means of heat to be used for cooking.

- How heat will be contained, i.e. heating appliances should be fixed securely on a firm non-combustible heat-insulating base, and surrounded on three sides by shields of fire resisting non-combustible material.

- Provision for ensuring there are no combustible materials or flammable liquids in close proximity.

- What fire fighting measures should/shall be in place.

- Hot catering appliances must not be left unattended whilst in use.

- Deep fat fryers – Any canopy/ventilation hood fitted to fryers should vent directly to atmosphere and an auto high temperature limit device should be fitted.

6.4 Straw / hay bales

- Straw bales must not be used inside marquees or other enclosed structures unless they have been treated with a proprietary brand of fire retardant and a notice to this effect being clearly displayed.

- Straw bales used externally must not be placed adjacent to marquees, buildings or equipment, which would constitute a fire hazard.

- Any loose straw should be contained within suitable receptacles, e.g. steel bins

6.5 Fire extinguishers

Types of extinguishers for particular categories of fire:

- Water extinguishers for fires involving solid carbonaceous materials - e.g. wood, paper, textiles

- Foam extinguishers can be used for where both solids and liquids fire risk exists ……… Aqueous Film Forming Foam (AFFF) is particularly suited to fight liquid spill fires such as petrol, oil, fats, paints etc.

- Dry powder extinguishers which work by smothering and cooling and are used for running fuel fires, gas fires and electrical fires ……… or

- Carbon Dioxide (CO2) extinguishers for flammable liquids and especially for electrical hazards

- A special Class 'F' extinguisher may be selected for use by caterers should hot fats be used within the food preparation process

General guidance on selection of extinguishers:

  - 1 x 9 litre water per 210m2 of floor area within a structure

  - Electrical risks – minimum 1 x 2 kg carbon dioxide

  - Vending Units – minimum 1 x 2 kg dry powder and one fire blanket

7: Electrical Safety

Power for the Show’s own needs is provided by generators loaned by one of the Exhibitors. Exhibitors /contractors provide their own generators. Outfeed cables from generators must be laid out by competent persons

7.1 General rules on electrical supply and equipment

- Large structures such as marquees erected by contractors shall have had their electrical systems inspected tested in accordance with BS7671 - Institute of Electrical Engineers Wiring standards with a current certificate being made available to confirm the requirement has been met.

- All electrical equipment must be in sound condition and be suitable for the type of use intended, e.g. IP 65 rated if used in damp or wet conditions, or where they could be.

- All equipment shall be connected to the means of supply through a Residual Current Device (RCD) having a maximum tripping current rating of 30 mA, and all cables and connections where not protected by a weatherproof structure shall be of such construction, or protected as necessary to prevent danger arising from exposure. Should this condition create difficulties with the operation of certain equipment the show’s electrical contractor should be consulted.

- All cables shall be of the correct rating for the potential load with no damage to the insulation.

- All electrical connections shall be suitable for external use.

- All supply cables shall where practicable be positioned so they are not liable to physical damage, e.g. not run across (on top of) roadways liable to heavy traffic or heavily populated door openings. Such cables must be suitably protected, e.g. wire armoured.

- Cable runs should be made with due consideration to the prevention of slip and trip hazards

- Socket outlets should not be overloaded and extension leads used only where really necessary and should not create a trip hazard.

- Spot checks will be carried out by show officials and any equipment found to be faulty will be immediately withdrawn from use

7.2 Exhibitors’ generators

- Exhibitors and Sponsors must notify the Show or Trade Stand Secretaries if it is intended to use their own generator on the showground. Such equipment may be subject to random checks by show officials throughout the period on site.

- Exhibitors or their contractors will have to provide evidence of inspection and testing in the form of a current test certificate for verification by the show’s electrical contractor or the show secretary prior to any connection.

- The maximum output of any generator brought onto site by exhibitors is limited to 5 kVA.

- Generators should be sited on a secure platform away from all flammable materials.

- One point of the generator output circuit should be earthed. Earthing should be by earth rods and the effectiveness of the earth shall be tested by the competent person who installs the generator.

- Fuel for generators must be stored in suitable sealed containers out of direct sunlight.

- Quantities of fuel must be kept to a minimum.

- Generators shall not be refuelled when they are running.

- Any generator that may be at risk of unauthorised access or interference or damage due to show activities must be suitably protected by suitable enclosure or physical barrier.

- Adequate caging of the exhaust outlet must be in place to prevent any person being burnt.

8: Temporary buildings and structures

Any temporary structure such as marquees and other temporary buildings, barriers/fences, gates, platforms, information/notice boards etc. that are assembled using connecting components must be soundly constructed, erected and safe for their intended purpose and shall be inspected and signed off on behalf of the Show by a competent person before use.

8.1 Marquees

- Larger temporary buildings (marquees) shall be erected in line with the Made Up Textiles Association’s MUTAmarq “Best Practice Guide for the Safe Use and Operation of Marquees and Temporary Structures” with erection (and dismantling) contractors being MUTAmarq accredited.

- The electrical installation for temporary buildings shall be installed, tested and maintained in accordance with the provisions of the IEE Regulations for Electrical Installations.

- Shall have adequate means of unobstructed access and egress, with due consideration for emergency exiting needs

- Shall have entrances and exits and exhibits positioned so as not to coincide with main guy lines and must be free of obstruction by tent pegs.

- Shall have any tent pegs in the vicinity of an entrance and exit suitably protected to avoid tripping and injury.

8.2 Barriers and fences as means of guiding or restraining

- Types of restraint will usually be dictated by specific activities, e.g. the type of exhibit.

- A single or double rope and post fence might be adequate for minimum protection, whereas a secure wire mesh or vertical barrier rail type fence will be needed where total public access is to be prevented.

- When it is deemed that single or double rope barriers may not be sufficient for a specific situation then any barrier/fencing used must be capable of withstanding any reasonably foreseeable loading, e.g. be of suitable design to contain and protect people, including small children.

8.3 High notice boards and flagpoles

- Sufficient space around notice boards should be provided in the event that tall structures are at risk of becoming a hazard due to high winds can be taken down quickly and easily.

- Structures and any flagpoles must be securely installed, be of adequate strength taking into account wind and other stresses and must not be erected in close proximity (within 6 metres) to overhead electric cables.

- The use of guy ropes and wire for flagpoles should be avoided, but, if they have to be used, the guyed area must be adequately fenced.

- Guy ropes and other means of securing that have not been installed by the Society’s approved contractors shall be inspected and signed off on behalf of the Society by a competent person before use

8.4 Inflatable structures

- Any activity associated with an inflatable structure or equipment must be supervised at all times by a competent person and appropriate safety notices be clearly displayed.

- An inflatable brought onto the showground for use shall have been tested under an accredited UK testing scheme (e.g. ADIPS or PIPA) with a current safety certificate issued by an independent examiner.

- Structures should be provided with an adequate anchorage and/or ballast system. Any anchorage points should be suitably protected where appropriate. The size, number and strength of anchorage points should be adequate for the structure and take into account likely wind loading.

9: Environmental Management – Sanitation, refuse/waste management and environmental nuisance

9.1 Sanitation

- Sufficient and suitable WC’s and urinals including adequate provision for disabled persons will be provided for, in line with general recommendations for such sized events and an estimation of numbers attending the show.

- Large event portable toilets are hired for the show and they are kept clean and hygienic throughout the show.

- Typically, events with a gate opening time of 6 hours or more will have a toilet provision in line with the following:

  - Females: 1 toilet per 100 females

  - Males: 1 toilet per 500 males, plus 1 urinal per 150 males

- Hand washing facilities should be provided at a ratio of 1 per five toilets with no less than one hand washing facility per ten toilets and include for suitable hand drying facilities.

9.2 Refuse, rubbish, waste:

- Waste bag stations are strategically positioned round the showground and all persons are expected to use them properly.

- Stewards will use their radios to contact the Showground control if bags are found to be overfull.

- Exhibitors are required to ensure the removal of rubbish from their stands on a regular basis to minimise safety and health hazards with particular attention being given to glass and tins/cans and food scraps. Note: In any failure to clear debris or refuse from stand sites, any cost for clearing up incurred by the Show will be re-charged accordingly.

- Should any exhibitor, contractor activities lead to the production of hazardous waste (e.g. oils, solvents chemical wastes pesticides, lead-acid batteries) in amounts that cannot be removed and disposed of properly by themselves, the Show Secretary and/or Showground Manager must be informed in good time in order for them to make any necessary special arrangements that may be required.

- Hazardous wastes should not be placed in with general wastes.

Note: any costs incurred by the Show Society with regard to the handling, sorting and disposal of hazardous waste that it has not been informed of, may be re-charged in full against the producer of the waste.

9.3 Environmental nuisance

- Typical examples of nuisance arising from events would include noise, dust and smoke.

- Whilst elevated levels of noise may be produced, the location and the hours that show is open for will minimise any adverse impact on the locality.

- Bonfires shall not be lit as a means of disposing of waste arising from the show or any other reason.

- As the event is held on fields it is highly unlikely that significant levels of dust will be produced.

10: Health hazards

Whilst there are number of health hazards associated with human contact with livestock the zoonoses most likely to be encountered in a show environment would be Escherichia coli (E coli) 0157 and Cryptosporidiosi. Accordingly, appropriate, practical precautions need to be adopted. These are detailed fully in the Woolsery Show Biosecurity Plan. In brief, such measures shall include:-

- Reducing so far as is reasonably practicable, opportunities for members of the public to contact build-ups of faeces.

- Providing sufficient and suitable warning and information notices.

- Providing adequate washing facilities (with running, hot water) close by to wherever contact with stock by the public is likely.

- Providing strategically positioned disinfection baths and brushes for footwear cleansing

    - Any veterinary medicines that have been authorised to be brought onto the showground must be stored securely, under the lock and key control of a/the veterinary practitioner.

    - The use of any substance containing toxic chemicals, including sheep dips to prepare sheep for showing, whilst on the show ground, is strictly forbidden.

11: Catering

- Professional caterers will be expected to carry out their duties in accordance with the Food Safety Act 1990 (as amended) and the Food Hygiene (England) Regulations 2005 and persons employed by them shall have had suitable and sufficient training.

- Caterers should be aware that Inspectors of the Environmental Health Departments may make inspections prior to, and during events, to ensure that food operators understand and comply with the relevant legislation.

- A food management diary should be in place and used.

- Food and drink must be described fairly and accurately so that the customer can understand what they are buying.

- Waste food/waste meat must not be used for animal feed.

11.1 General catering controls and precautions

- Hands must be washed after handling, raw foods or waste, and after going to the toilet.

- Use potable water only.

- Wear a clean apron or overall to protect food from contamination.

- There should be enough tongs, utensils boards, containers and surfaces to avoid cross-contamination.

- Fridge temperatures must be kept below 8°C

- Store raw and cooked foods separately in fridges

- Jewellery, other than plain bands, should be removed before handling food and hair should be covered or tied back

- Ensure there are sufficient waste receptacles, that they have closable lids and that they are not allowed to overflow

- Ensure that temperature probing or other adequate checks are made when cooking and particularly re-heating food

- Barbequing – additional care and caution is required for barbeque food as the heating is much less predictable than oven/range cooking.

- Hot oils must be allowed to cool sufficiently before draining

- Demonstration knives, kitchen equipment etc. must not be left lying about due to the risk to children

- Hot pans and heated surfaces must be protected.

12: Animals, Livestock and Equestrian events control

12.1 Dogs

- Must be kept on a lead at all times.

- All dog owners must pick up and dispose of faeces safely

- Must NOT be left unattended or in vehicles.

- If a dog is found to be at risk, call for a Police Officer or other witness.  Call /radio the Secretary’s Tent for the Show Vet to attend and for a call out for the owners.

- Forcible entry to a vehicle may be necessary without liability or damage to the Show and its personnel.

- Make a note of the conditions and temperature if possible. If there is time photograph the distressed animal. An incident report form must be completed in the Secretary’s Tent.

12.2 General Livestock

- Exhibitors are entirely responsible for the safe handling of their animals and the suitability of any equipment brought onto the showground.

- The movement of Cattle and Sheep and must be kept to a minimum and when movement required, this must be strictly controlled and stewarded including the movement of stock to and from judging rings.

- Safe routes shall be established for the movement of cattle from holding areas to display rings so as to keep members of the public at a safe distance from livestock being transferred. This cordoning may be provided by the use of temporary barriers or by the use of stewards.

- Exhibitors should be aware that spectators are unlikely to be familiar with the characteristics of animals and unaware of the potential danger that they might be in or which they might create by their own actions.

- Where animals are in pens, care must be taken to ensure that the means of securing such enclosures are in good order and they are properly closed.

- Exhibitors should minimise the movement of stock and take particular care to ensure, should any animals have to be halter lead that this is done by a person who is competent with training and experience.

- When animals are being handled for preparation etc., the safety of spectators/members of the public close by must be a primary consideration.

- Wherever there is likelihood of public contact with animals, washing and/or disinfection facilities shall be provided.

12.3 Sheep management

- Under DEFRA licence the showing of sheep in the Livestock Field and use of the Livestock Lorry Park, is authorised but Maedi Visna (MV) accredited and non-MV accredited sheep must always be kept separated by at least two metres distance. Note: This licence does not allow sheep to be ‘walked’ out of a licensed area.

- MV accredited and non MV accredited and must not be allowed to come into contact at any time during the show.

- DEFRA ARAMS1 movement forms. It is essential that movement forms be completed for all consignments of sheep to the show. These must include the individual identification number for each sheep and not just the flock number. An ARAMS1 shall be required for the journey to the show and return journey.

- Maedi Visna Accreditation - Show Stewards are responsible for ensuring that exhibitors of MV accredited Sheep have a current, fully completed green SAC MV certificate before any animals are unloaded.

12.4 Horses

- Horses must not be ridden, exercised or schooled in the car parks, trade stand avenues or other areas to which the general public has access, except within the confines of the ‘Horse Area’.

- No one is allowed in an exercise or collecting ring who is not a rider or bona-fide groom.

- Anyone riding a horse or pony on the showground must wear protective headgear of a standard approved by their appropriate governing body, specifically the British Horse Society.

- A protected corridor (barriers) shall be established for the movement of horses from the collecting ring to the Main Ring.

12.5 Escaped animals

- The Woolsery Show Biosecurity and Incident Management Plans fully address actions in the event of an animal escaping. In brief, all available stewards should assist handlers in recapture and in ensuring the safety of the public.

- All gates in the vicinity shall be closed to prevent escape on to the public highway, even at the expense of admissions to the ground.

- Once apprehended the relevant Chief Steward in discuss with the Show Vet shall decide whether the animal should remain on the show field.

12.6 Judging

During judging the following conditions should apply

- Ensure separate routes to rings and on return to dedicated pens

- Ensure separation of MV accredited and non-accredited sheep

- Ensure MV accredited sheep are judged and mouthed first

- MV accredited sheep must be lead by a halter

- Examination of mouths should be carried out by handlers

- If a judge mouths sheep, then disinfectant must be used between each mouthing.

13: Security

- Cash handling gate receipts presents a risk of theft/attack when handling cash in any amount.

- There should always be a minimum of two stewards at entrance points where paying customers enter the event and there shall be a means of immediately communicating with the show officials and senior stewards provided for.

- Monies collected should be transferred at intervals to the Show Treasurer for sage keeping

14: Plant, machinery and vintage vehichles/equipment

- Plant and machinery will be used on the show ground for set up prior to, during and after the show for take down.

- Any person operating a vehicle must be competent and have supporting evidence to operate this type of vehicle.

- All responsibility for damage, however caused, remains with the driver of the vehicle at the time the damage occurs.

14.1 General machinery/plant safety

Plant and machinery must only be operated and demonstrated after ensuring that adequate precautions are taken to protect the operator and bystanders.

Such precautions will include:-

- All machinery for display or exhibiting with moving parts must have any parts that a person could foreseeably come into contact adequately guarded. This would typically include exposed shafts, belts and pulleys and gears. Hydraulically supported equipment must be mechanically locked or braced to prevent collapse. Knives, blades, spikes and other sharp edges are to be guarded and all engines immobilised and horns disconnected.

- Machinery must only be operated or demonstrated in areas adequately fenced off from the public.

- Machinery operators must be prepared to stop the equipment should unauthorised persons enter fenced off areas.

- Should equipment be protected by a fail-safe valve system, a notice indicating this should be shown on the machine along with evidence of regular machine inspection/maintenance.

15: Work at height

- Work such as the erection of temporary structures should be planned so that as much of the work as is reasonably practicable, may be carried out at ground level, e.g. pre-assemble as much as possible before lifting and positioning so as to reduce the risk a fall from height.

- Where mechanical access equipment is used it shall have evidence of examination by a competent person under the Lifting Operations and Lifting Equipment Regulations (LOLER) and inspection under the Provision and Use of Work Equipment Regulations (PUWER) and only persons who are competent through appropriate training shall operate the machine.

- Such work will be carried out in accordance with established safe operating conditions for the machine selected and in line with manufacturer’s instructions.

Note: Articulating MEWPs should not to be used for lifting heavy materials or equipment, they are only designed as a means of access to height.

- Scissor lifting machines can be used for the lifting of materials or equipment not exceeding the manufacture’s maximum lifting capacity for the machine.

- Ladders and stepladders – Must be fit for purpose and in sound condition, be of wood or fibreglass construction if working under or close to electricity.

- Ladders must only be used for low level, low risk, short duration, light duty working.

16: Lifting operations and lifting equipment

- Any complex lifting operations with significant residual risk as identified by risk assessment will require a lift plan being produced and provided in sufficient time for review by the Show’s Safety Advisor and other competent person representing the society before commencement of the operation.

- Lifting equipment used will have current certification as evidence of examination by a competent person within the last twelve months.

- Lifting accessories (e.g. chains, slings, shackles) will have current certification as evidence of examination by a competent person within the last six months and the safe working load identified by an appropriate means of marking, e.g. tagging or stamping.

- Exhibitor or contractors using vehicles with tails lifts must be able to demonstrate evidence of the tail lift being examined by a competent person within the 6 months prior to use. Vehicle hire companies should be requested to provide this evidence when hiring.

17: Manual handling

The setting up and break down phases of the show in particular are periods where manual handling activities occur. However, before starting such work always assess whether manual handling can actually be avoided, is there a better way of doing it, i.e. can mechanical handling equipment (e.g. forklift truck) and other handling aids be used.

Typical tasks that will involve manual handling are the use of (timber) post drivers for erecting posts … ground anchoring of scaffold poles … pulling power cables … manual erection of signs … handling/ positioning of straw bales.

Where assessment determines that manual handling cannot be avoided then planning and assessment of the work is required. For general manual handling tasks apply the principles of TILE as an assessment tool for identifying risk and what precautions need to be implemented

- Assess the TASK itself –

How often is the task performed and how long for

Could there be unpredictable movement of the load

Does the task involve:-

- Holding loads away from body

- Strenuous pushing and pulling

- Twisting

- Stooping

- Reaching upwards / Large vertical movements

- Carrying, pushing or pulling over long travel distances.

- Assess the INDIVIDUAL’ lifting capacity and fitness of each person, considering physical dimensions and capacity such as height, weight and strength.

- Will the work require specific capability, e.g. above-average strength or agility or call for special information or training;

- For ‘team lifting’ it should be understood that the load that a team can handle safely is less than the sum of the loads that the individual team members could cope with when working alone.

As an approximate guide, the capability of a two-person lift is two-thirds the sum of their individual capabilities and for a three-person team the capability is half the sum of their individual capabilities … Teams of more than four members are unlikely to work successfully.

- Assess the LOAD to be lifted or moved, considering such factors as:-

- How heavy is it – is there any information on the load as to weight.

- Where is the centre of gravity?

- What shape is it … is it bulky or unwieldy … Is it unstable/unpredictable … is it difficult to grasp.

- Does it have sharp/jagged edges, do gloves need to be worn.

- Will assistance be required?

- Assess the ENVIRONMENT being worked in, considering such factors as:-

- Is the ground flat/level / Are there gradients.

- Is the ground clear of slip and trip hazards, are there space constraints on posture.

18. Children's Entertainment

- Entertainment devices must comply with 'HSG175 Fairgrounds and Amusement Parks -Guidance on Safe Practice'. They must be run by qualified adults, provided with the necessary safety fences and operated within the designated areas.

- Inflatable play equipment must have an up to date ADIP/PIPA (or equivalent)

inspection tag/certificate.

- Refer to inflatable temporary structures under Section 8.4

- Documentation should be available on site. The Show reserves the right to audit this documentation.

19. Smoking

- Smoking is not permitted in any marquee or other structure erected for use on show site, including toilets.

- Smoking is also not permitted in any area where hay, straw or other bedding is stored. If smoking in any other area please ensure that you dispose of cigarette ends safely and without causing litter or the potential for ignition.

20. Communications

- Radio communication is available to specified Show Stewards and personnel - a list of radios and channels is available from the Show Secretary's Tent.

- As a backup, a list of mobile phone contact numbers is also available for the Executive, the Incident Management Team and Key Officials (see Annex 1)

- In cases of an EMERGENCY the Incident Management Team Manager call 01237 441996 (out of show hours) or 07876 722488

- To contact the Show Secretary call 01409 240328 or 07595 919006

- To contact the Trade Stand Secretary call 01237 441996 or 07748 880595

Other contact numbers can be found in Annex 1

Emergency Contact List						Annex 1

| Position | Name | Mobile Number | Reason | Radio |
| --- | --- | --- | --- | --- |
| Chairman | Pat Martin | 07587 144280 | All |  |
| Vice Chairman | Tony Lang | Via Secretary | All |  |
| Patron | John Rous | Via Secretary | Site issues |  |
| Secretary | Andrée Carter | 07595 919006 | All |  |
| H&S and Incident Management | James Weeks | 07876 722488 | H&S and Incident Management Team (IMT) |  |
| Treasurer | Brian Butler | 07980 988301 | IMT & Finance |  |
| Show Yard Director | Derek Lott | 07940 855142 | IMT & Show Day Issues |  |
| Deputy Show Yard Director | Jonny Furse | 07793 526432 | Main Ring & Show Day Issues |  |
| Biosecurity | Robert Dennis | 07470 284400 | All Animal Welfare Issues ARAMS/ Cattle Passports etc |  |
| First Aid | Carl Williamson | 07865 662200 | All Health Issues |  |
| Vet | Mark Shepherd | Via Secretary | All Veterinary Issues |  |
| Farrier | Danny Roberts | 07813 981035 | Shoeing |  |
| Chief Cattle Steward | Guy Ley | Via Secretary | All Cattle Issues |  |
| Cattle Steward | David Pomeroy | 07585 972470 | All Cattle Issues |  |
| Chief Sheep Steward | Gerald Ley | 07984 904556 | All Sheep Issues |  |
| Trade Stand & Local Crafts Secretary | Donna Weeks | 07748 880595 | All Trader Issues |  |
| Handicraft Secretaries | Florence Ley Elaine Burrow | 07969 011162 | All Handicraft Issues |  |
| Food & Farming Tent Secretary | Carol Fletcher | 07836 254452 | All Food & Farming Traders |  |
| Sheep Tent Secretary | Mike & Dee Priest | tbc | All Sheep Exhibits |  |
| Dairy Tent Secretary | Sarah Huxtable | 07507 295641 | All Dairy Exhibits |  |
| Horse Lorry Parking | Richard Furse | 07766 381410 | All Horse Lorry Issues |  |
| Show Jumping | Christine Buckpitt | 07814 044483 | All Issues Ring 5 |  |
| Car Parking | Jon Cleave | 07837 200767 | All Parking Issues |  |
| Gate | Bob Hicks | 07773 795823 | Admission and entrance/exit gate |  |
| Horse Secretary | Caroline Furse | 07803 965252 | All Results |  |
| Sheep Secretary | Mandy Walter | 07773 400312 | All Results |  |
| Cattle Secretary | Emma Hart | 07920 063194 | All Cattle Issues |  |
| Cups and Trophies | Candy Jacklin & Nicky Williams | Via Secretary | Cups and trophies |  |
| Inter Hunt Relay | Mike Ward | 07970 419622 | All Hunt issues |  |
| Vintage | Bonham Jewell | Via Secretary | Vintage |  |

Annex 2

Primary Legislation relevant to the show:

Health and Safety at Work Act 1974 (General duties)

Management of Health and Safety at Work Regulations 1999 (Risk assessments)

Reporting of Injuries, Diseases and Dangerous Occurrences Regulations 1995 (RIDDOR)

Regulatory Reform (Fire Safety) Order 2005

Electricity at Work Regulations 1989

Control of Substances Hazardous to Health Regulations 2002 (COSHH) (Hazardous substances and biological hazards, including those that may be transferred from animals to humans)

Provision and Use of Work Equipment Regulations 1998 (PUWER) (Plant and machinery)

Health and Safety (First Aid) Regulations 1981

Work at Height Regulations 2005

Lifting Operations and Lifting Equipment Regulations 1998 (LOLER) (Use of any equipment for the mechanical lifting and placement of equipment, structures etc. and the accessories used, e.g. chains, shackles and attachments/items used to raise or lower people.

Other:

Environmental Protection Act 1990 (waste disposal, nuisance)

Traffic Signs Regulations and General Directions 2002

The Traffic Management Act 2004 (duty on traffic authorities)

Food Safety Act 1990 (as amended)

Food Hygiene (England) Regulations 2005

The Purple Guide, Preventing or Controlling ill health from animal contact at visitor attractions Industry Code of Practice version 1 June 2012.

Annex 3